## Sheet1
Date |  | Project Name | Funding Source CC = Controlled Maintenance CP = Capital Construction FF = Federal Funds IH = In-house OT = Other | Bidding Method AFB or RFP | Project Delivery Method CMGC = Construction Manager/General Contractor CSBV = Competitive Sealed Best Value DB = Design Build DBB = Design/Bid/Build IPD = Integrated Project Delivery | Rationale for Delivery Method: Project Schedule Impacts/Cost Limitations/Complexity of Work | Waiver Attached or Not Applicable | Awarded Contractor | Contract Amount / Fee ($) | Date Contract / NTP Executed
Project Number
02/03/2020 | 2020-090M19 | HVAC Replacement & Controls Upgrade | CC | AFB | DBB | Design critertia is striaght-forward. Replace 19 rooftop units on Spruce, Elm, and Cottonwood Hall on main campus. The new RTUs shall be more efficient units that will improve utility and maintenance costs. | N/A | TBD | TBD | TBD
8/14/2019 | 2019-104 | Poplar Hall | CP | AFB | DBB | Design criteria is straight-froward. 5,000 sq ft pre-engineered metal building to house agriculture-related instructional programs.Includes classroom, computer lab, shop, faculty offices, restrooms and support. | N/A | Buildings by Design | 1437302 | 10/15/2019 & 9/19/19
06/27/19 | 2018-059M19 | Repair/Replace Damaged Walks, Stairs, and ADA Ramps | CC | AFB | DBB | Design criteria is straight-forward. Repair and replace various exterior damaged or non ADA compliant sidewalks, stairs, ramps, and handrails around Cottonwood, Aspen and Spruce Halls on the Morgan Community College Campus. Remediate drainage issues around the building. Deaccession state artwork in the area. | N/A | Taylor Kohrs | 470099 | 6/26/2019 & 07/17/2019
05/22/2019 | 2019-102 | Limon Center Tenant Finish | CP | AFB | DBB | Design criteria is straight-forward. Tenant finish of 3,000 sq ft. of leased space located in Ben's Family Pharmacy building in Limon, CO. Program includes classrooms, offices, restrooms, support and 700 sq ft of unfinished space. | NA | Growling Bear Co., Inc. | 367202 | 07/30/2019 & 07/02/2019
3/5/19 | 2019-042M18 | Electrical Upgrades for Cottonwood and Aspen Halls | CC | AFB | DBB | Design criteria is straight-forward. Replace switchgear, main load breakers and istribution panels. Relabel panel circuits in Cottonwood/Aspen Halls. Budget has been established and approved; project will be completed within budget. | N/A | Morton Electric, Inc. | 345297 | 3/4/2019 & 3/25/2019
9/3/14 | 2009-162M14 | Improve Campus-Wide Safety and Security | CC | AFB | DBB | Design criteria is straight-forward. Provide security upgrades, rekey the main campus and replace windows/doors in Cottonwood/Aspen Halls. Budget has been established and approved; project will be completed within budget. | N/A | Schauer Construction Company, Inc. | 457700 | 5/29/15 & 6/1/15
4/28/14 | MCC201401 | Birch Hall, Welder Training and Campus Storage Facility | IH | AFB | DBB | Design criteria is straight-forward. New facility that will replace damaged storage structure which has been demolished and an existing leased facility for instructional program. Project must be complete before lease expires. Budget has been established and approved; project will be completed within budget. | N/A | Schauer Construction Company, Inc. | 787694 | 7/1/2014 & 7/1/2014